## Disclaimer
DISCLAIMER
Copyright 2019, Airworthiness Certification Services, Inc. (ACS) in partnership with the Avionics Certification Academy.
All rights reserved.
These Checklist Templates are perpetually licensed for a single company, for the site and/or project team who initially purchased. The purchaser can use the Checklist Templates, or any customized variant of them, on as many projects as desired. The Checklist Templates may not be shared outside of the purchasing company with the exception of interactions with customers and program auditors. The Purchaser agrees to these terms as part of the sale. If a worldwide Corporate License is desired, which provides unlimited access for all sites and project teams within a company, contact info@Airworthinesscert.com for details and a quote.
This Checklist Template is proprietary to ACS. and should not be distributed or copied in its original format without written permission. It is to be used solely as the basis of documentation for the purchaser of this Checklist Template. Also, it should not be viewed as FAA opinion or regulatory guidance and presents only opinion and interpretation of FAA information by ACS.
All references to DO-178C and/or DO-254 material are copyrighted by and used with permission from:
RTCA, Inc.
1150 18th Street NW, Suite 910
Washington, DC 20036
(202) 833-9339
www.rtca.org
ACS hereby disclaims all warranties and conditions with respect to these Checklist Templates, either express, implied or statutory, including, but not limited to, the implied warranties and/or conditions of merchantability, of satisfactory quality, of fitness for a particular purpose, of accuracy, or quiet enjoyment, and non-infringement of third party rights. ACS does not warranty against interference with clients enjoyment of the Checklist Templates, that the functions contained in the Checklist Templates will meet the client’s requirements, that the Checklist Templates will be error-free or that defects in the Checklist Templates will be corrected.
No oral or written information or advice given by ACS or by an ACS authorized representative shall create a warranty should the Checklist Templates prove defective, client assumes the entire cost of all necessary servicing, repair or correction.
Downloading and using these Checklist Templates signifies you have read and accepted these conditions.
Please direct all questions or concerns to:
Airworthiness Certification Services
25327 SE Mirrormont Blvd Issaquah WA 98027
Phone: 206-226-6561, email: info@airworthinesscert.com
NOTE: YOU MAY REMOVE THIS PAGE FROM YOUR CHECKLIST TEMPLATES AFTER READING THIS DISCLAIMER

## README
The purpose of the Transition to Conceptual Design Review is to ensure all the activities and criteria required to complete the Requirements phase and to produce the inputs to Conceptual Design have occurred, prior to starting this phase of the Hardware Life Cycle. You want to ensure all requirements are reviewed and baselined prior to being used in the design and implementation phases.
It is typically lead by Process Assurance.
It is typically performed during the program when you are ready to begin using the requirements to start development of the design. You want to ensure you are working on mature, compliant requirements that are under proper control, as you begin designing.
The data that is reviewed includes HRD and trace data.
Use of Templates: These templates are tailored by DAL. You only need to respond to those questions that include an X in the column under the DAL of your project. Data filtering has been added so that you can click the arrow next to the DAL of your project, and then put a checkmark only by the option that says "X". This will then only display the questions pertinent for that DAL.

## Revisions
Rev. | Reason/Description | Requested/ Changed By | Date

## Criteria To Start ConceptDesign
Hardware Transition to Conceptual Design Review Checklist
Project Name:
Document(s) under review: (This should specify the document number and version)
Supporting documents: (This should include the documents used as reference or input to support the review. )
Reviewer Name: | [7 empty] | Review Date:
# | Checklist Item | DO-254 or Other Guidance Reference | DAL |  |  |  | Compliance | Remarks (The reviewer should include a reference to the information, evidence of the pass or failure in this column, and justification for N/A)
|  |  | A | B | C | D | Y/N/NA
1 | Have design constraints (due to production processes, standards, procedures, technology, design environment and design guidance) been identified? | 5.1.2.3 | X | X | X | X
2 | Have all hardware item high-level requirements and derived requirements been developed? | 5.1.1.1; 5.1.2.4 | X | X | X | X
3 | Have all derived requirements and the requirements that are traceable to the upper-level requirements been independently validated (especially with respect to safety) at some hierarchical level by review, analysis or test? | 6.1.2.2; AC20-152A CD-3 | X | X
4 | Have all derived requirements and the requirements that are traceable to the upper-level requirements been validated (especially with respect to safety) at some hierarchical level by review, analysis or test? | 6.1.2.2; AC20-152A CD-3 |  |  | X | X
5 | Do the hardware requirements include the expected behavior of the design in response to abnormal and boundary conditions (i.e., Robustness Requirements)? | AC20-152A CD-7 | X | X
6 | Has a requirements review been held to ensure the acceptability of requirements and compliance to the guidelines of 6.3.3.1? | 6.3.3.1 | X | X | X | X
7 | Have derived high-level requirements been provided to the System Safety Assessment Process? | 5.1.1.2; 5.1.2.5; 6.1.2.3 | X | X | X | X
8 | Have requirement omissions and errors been provided to the appropriate process for resolution? | 5.1.1.3; 5.1.2.7 | X | X | X | X
9 | Are the requirements traceable to system requirements? Are derived requirements traceable as far as possible through the hierarchical levels? | 5.1.2.8 | X | X | X | X
10 | Are the requirements complete and compliant with respect to system requirements? | 6.1.2.4; 6.1.2.5; AC20-152A CD-3 | X | X | X | X
11 | Has traceability been established between the derived and high-level hardware requirements and the validation activities and results? | 6.1.2.6 | X | X | X | X
12 | Have requirement omissions and errors from the validation process been fed back to the appropriate process for resolution? | 6.1.2.7 | X | X | X | X
13 | If COTS IP is used, do the requirements include all the IP functions, including unused ones for deactivation? | AC20-152A IP-5 | X | X | X
14 | Have the planned transition criteria for entering the Hardware Conceptual Design Process as identified in the PHAC and Hardware Development Plan been satisfied? | 3.2 | X | X | X | X