## Disclaimer
DISCLAIMER
Copyright 2019, Airworthiness Certification Services, Inc. (ACS) in partnership with the Avionics Certification Academy.
All rights reserved.
These Checklist Templates are perpetually licensed for a single company, for the site and/or project team who initially purchased. The purchaser can use the Checklist Templates, or any customized variant of them, on as many projects as desired. The Checklist Templates may not be shared outside of the purchasing company with the exception of interactions with customers and program auditors. The Purchaser agrees to these terms as part of the sale. If a worldwide Corporate License is desired, which provides unlimited access for all sites and project teams within a company, contact info@Airworthinesscert.com for details and a quote.
This Checklist Template is proprietary to ACS. and should not be distributed or copied in its original format without written permission. It is to be used solely as the basis of documentation for the purchaser of this Checklist Template. Also, it should not be viewed as FAA opinion or regulatory guidance and presents only opinion and interpretation of FAA information by ACS.
All references to DO-178C and/or DO-254 material are copyrighted by and used with permission from:
RTCA, Inc.
1150 18th Street NW, Suite 910
Washington, DC 20036
(202) 833-9339
www.rtca.org
ACS hereby disclaims all warranties and conditions with respect to these Checklist Templates, either express, implied or statutory, including, but not limited to, the implied warranties and/or conditions of merchantability, of satisfactory quality, of fitness for a particular purpose, of accuracy, or quiet enjoyment, and non-infringement of third party rights. ACS does not warranty against interference with clients enjoyment of the Checklist Templates, that the functions contained in the Checklist Templates will meet the client’s requirements, that the Checklist Templates will be error-free or that defects in the Checklist Templates will be corrected.
No oral or written information or advice given by ACS or by an ACS authorized representative shall create a warranty should the Checklist Templates prove defective, client assumes the entire cost of all necessary servicing, repair or correction.
Downloading and using these Checklist Templates signifies you have read and accepted these conditions.
Please direct all questions or concerns to:
Airworthiness Certification Services
25327 SE Mirrormont Blvd Issaquah WA 98027
Phone: 206-226-6561, email: info@airworthinesscert.com
NOTE: YOU MAY REMOVE THIS PAGE FROM YOUR CHECKLIST TEMPLATES AFTER READING THIS DISCLAIMER

## Revisions
Rev. | Reason/Description | Requested/ Changed By | Date

## README
The purpose of the Transition Review for Test Readiness is to ensure that the test procedures and test environment meet the standards, have been reviewed, and are baselined prior to starting verification for formal credit. Tool qualification should be complete as well. In addition, the test environment should be audited and controlled.
It is typically lead by Process Assurance.
It is typically performed during the program when the team is ready to run the tests for certification credit.
The data that is reviewed includes the HTP, HCI, HECI, Tool Qualification, and trace data (for trace to test).
Use of Templates: These templates are tailored by DAL. You only need to respond to those questions that include an X in the column under the DAL of your project. Data filtering has been added so that you can click the arrow next to the DAL of your project, and then put a checkmark only by the option that says "X". This will then only display the questions pertinent for that DAL.

## Criteria to Test for Credit
Hardware Test Readiness Review Checklist
Project Name:
Document(s) under review: (This should specify the document number and version)
Supporting documents: (This should include the documents used as reference or input to support the review. )
Reviewer Name: | [7 empty] | Review Date:
# | Checklist Item | DO-254 or Other Guidance Reference | DAL |  |  |  | Compliance | Remarks (The reviewer should include a reference to the information, evidence of the pass or failure in this column, and justification for N/A)
|  |  | A | B | C | D | Y/N/NA
1 | Has a hardware item been produced that implements the hardware detailed design using representative manufacturing processes? (Note that this may include procurement, kitting, build, inspection and test.) | 5.4.1.1; 5.4.2.1 | X | X | X | X
2 | Is the hardware item implementation, assembly and installation data complete? | 5.4.1.2 | X | X | X | X
3 | Have derived requirements identified during Implementation been fed back to the detailed design process or other appropriate processes? | 5.4.1.3; | X | X | X | X
4 | Has a review of the design tool reports taken place (e.g. synthesis and place and route reports) to ensure that the tool execution to generate its output was performed correctly? | AC20-152A | X | X | X | X
5 | Has traceability been established between hardware requirements, the implementation, and the verification procedures and results? | 6.1.2.2 | X | X
6 | Has traceability been established between hardware requirements and the verification procedures/results? | 6.1.2.2 |  |  | X | X
7 | Has acceptance test criteria been established that is consistent with the design assurance levels of the hardware functions and does it include the following? 1. Key attributes to be tested. 2. Pass/fail criteria for each key attribute. 3. Any test constraints. 4. Substantiation of the key attributes and pass/fail criteria. 5. Coverage of design aspects necessary to meet the safety requirements. 6. Assessment data that shows that the test criteria have been properly implemented based on the actual test procedures and associated test results. | 6.1.2.3; 10.5 | X | X | X | X
8 | Has each requirement been appropriately validated (especially with respect to safety) at some hierarchical level by review, analysis or test? | 6.1.2.2 | X | X | X | X
9 | Has the review, analysis or test results associated with the validation of each requirement been shown to be correct, and have discrepancies explained? | 6.1.2.2 | X | X | X | X
10 | Have derived requirements been evaluated for their impact on safety? | 6.1.2.3 | X | X | X | X
11 | Have derived hardware requirements been evaluated for completeness with respect to the system requirements? | 6.1.2.4 | X | X | X | X
12 | Have derived hardware requirements been evaluated for correctness with respect to the system requirements? | 6.1.2.5 | X | X | X | X
13 | Has traceability between the derived hardware requirements and the validation activities and results been established? | 6.1.2.6 | X | X | X | X
14 | Have requirement omissions and errors been fed back to the appropriate process for resolution? | 6.1.2.7 | X | X | X | X
15 | Have requirements that need a verification activity been identified, and has the hierarchical level of verification been identified? | 6.2.2.1 | X | X | X | X
16 | Have appropriate verification methods, such as tests, simulation, prototyping, analyses and reviews, been selected and performed with independence for each requirement needing verification? | 6.2.2.2; A-1 | X | X
17 | Has each verification case and procedure been reviewed to confirm that it is appropriate for the requirements to which it traces and that the requirements are correctly and completely covered by the verification case and procedure? | AC20-152A CD-5 | X | X | X | X
18 | Have appropriate verification methods, such as tests, simulation, prototyping, analyses and reviews, been selected and performed for each requirement needing verification? | 6.2.2.2 |  |  | X | X
19 | Has Verification coverage analysis been performed to determine each requirement has been verified at some hierarchical level by review, analysis or test? | 6.2.2.4.a | X | X | X | X
20 | Has Verification coverage analysis been performed to determine the review, analysis or test of each requirement is appropriate for verifying the requirement, especially with respect to safety requirements? | 6.2.2.4.b | X | X | X | X
21 | Has Verification coverage analysis been performed to determine the review, analysis or test results associated with the verification of each requirement are correct and that discrepancies between actual and expected results are explained? | 6.2.2.4.c | X | X | X | X
22 | Have the results of the verification activities been documented? | 6.2.2.5 | X | X | X | X
23 | Have omissions and errors discovered during Verification been fed back to the appropriate process for resolution? | 6.2.2.6 | X | X | X | X
24 | Has each requirement to be validated or verified by test (including environmental qualification test) been identified? | 6.3.1.1 | X | X | X | X
25 | Has the testing stimulus, sequence and test conditions, such as item ambient temperature and applied voltage, been defined for each test? | 6.3.1.2 | X | X | X | X
26 | Have pass/fail criteria and a method for recording the results been defined prior to test execution? | 6.3.1.3 | X | X | X | X
27 | Has the complete identification of the test equipment and calibration date for each been recorded? | 6.3.1.4 | X | X | X | X
28 | Has the configuration identity of the hardware item being tested been recorded? | 6.3.1.5 | X | X | X | X