## Worksheet1
item_id | prid | dateopened | status | openedby | title | product | criticality | source | discipline_assigned | assignedto | target_date | close_date | description | problemfoundin | correctiveaction | fixed_in | verification | feedback | notes | meeting_id | safetyrelated | datemodified | archive_id | referenced_artifacts | archive_revision | archive_version
1040484407 | 1 | 2020-09-23 05:00PM PDT | Closed | test_3@airworthinesscert.com | When operating in environments in excess of 100c communications fails. | Pump | Type 0 - Failure (Safety Impact) | Quality Assurance | Engineering | test_4@airworthinesscert.com | 2020-09-30 05:00PM PDT | 2020-09-30 05:00PM PDT | When operating in environments in excess of 100c communications fails. Add cooling fan or heat sink. | Pump Monitoring Hardware |  | Board Rev 0.3 |  | [TM] Heat Sink added. Please verify. [TM] Increased Heat sink size. Please verify. | [QA] Failed at 110c. Please Fix. [QA] Verified. Heated board to 120c and communmication port still worked. |  | true |  |  | {"documents":[618827550],"source-codes":[61308248,61308248],"test_procedures":[273280319,273280319],"other":["New PR Attachment File"]} | a | 1.01
0 | 2 | 2020-09-23 05:00PM PDT | Open | test_3@airworthinesscert.com | Not Alerting on Over Pressure. | Pump | Type 0 - Failure (Safety Impact) | Quality Assurance | Engineering | test_4@airworthinesscert.com | 2020-09-30 05:00PM PDT |  | When there is a communications error on the serial port, an over presseure alert gets lost. If there is a communication failure, retry at least 3 times. | Pump Monitoring | [6 empty] | true |  |  | {} | a | 1.01
1031435507 | 3 | 2020-09-30 05:00PM PDT | Open | test_3@airworthinesscert.com | Timing out reading serial port. | Pump | Type 0 - Failure (Safety Impact) | Quality Assurance | Engineering | test_4@airworthinesscert.com | 2020-09-30 05:00PM PDT |  | If the hardware takes longer than 3ms to respond the software times out. Up timeout to 20ms. | Pump Monitoring Software | [6 empty] | true |  |  | {} | a | 1.01